## TOC
Tables of Contents
Worksheet | Description
Estimates | Create time and scope estimates based on formulas and historical data
Status | Create a project status based on Project activities
Activity list | BA activity list with sharepoint codes
Size | Project size descriptions
Calculations | Various project formulas
Templates | List of project templates and checklists
Stakeholders | List of project stakeholders
Create a table of contents for your tooklit.

## Estimates
| Item | Deliverable | Create/Use | Level/Weight | Time (H) |  | Totals | Entre time estimates here
1 | Study Phase | [7 empty] | Days (working) | Hours per week (working) |  | Actual Hours
1.1 | Strategic Planning | [6 empty] | 1 day | 1 | 6 |  | 6
| Strategic Plan |  | 0 | 1 | 35 |  | 0 | 1 week | 5 | 6 |  | 30
| Strategic Goals |  | 0 | 1 | 7 |  | 0 | 1 month | 20 | 6 |  | 120
[8 empty] | 3 months | 60 | 6 |  | 360
1.2 | Enterprise Analysis | [6 empty] | 6 months | 120 | 6 |  | 720
| Business Base | Yes | 1 | 1 | 10 |  | 10 | 1 year | 240 | 6 |  | 1440
| High-Level Description |  | 1 | 1 | 1 |  | 1
| Project Charter | Yes | 1 | 0.5 | 21 |  | 10.5
| Statement of Work | Yes | 1 | 1 | 7 |  | 7
| Request for Proposal | Yes | 0 | 1 | 0 |  | 0
| Outsource Development Decision | [5 empty] | 0
1.3 | Project Management | [5 empty] | 0
| Project Checklist |  | 1 | 1 | 2 |  | 2
| Status meetings |  | 1 | 1 | 10 |  | 10
| Status reports |  | 1 | 1 | 10 |  | 10
| Project Plan | Yes | 1 | 1 | 7 |  | 7
| Project Budgets |  | 1 | 1 | 3.5 |  | 3.5
| Project timelines |  | 1 | 1 | 3.5 |  | 3.5
| Manage Resources |  | 1 | 1 | 7 |  | 7
| Change Management Plan | Yes | 1 | 1 | 7 |  | 7
| Risk Management Plan | Yes | 1 | 1 | 7 |  | 7
| Work Breakdown structure | Yes | 1 | 1 | 7 |  | 7
2 | Implementation Period | [5 empty] | 0
2.1 | Requirements | [5 empty] | 0
| Approval to start Reqquirements Gathering |  | 1 | 1 | 0.5 |  | 0.5
| Project Sponsor Meeting |  | 1 | 1 | 2 |  | 2
| Requirements Brainstormign session |  | 1 | 1 | 3 |  | 3
| Requirements Elicitation |  | 1 | 1 | 21 |  | 21
| Research |  | 1 | 1 | 70 |  | 70
| Requirements Activities |  | 1 | 1 | 7 |  | 7
| Requirements Management Plan (RPM) | Yes | 1 | 1 | 7 |  | 7
| Requirements Analysis |  | 1 | 1 | 14 |  | 14
| Context Diagram (Scope) |  | 1 | 1 | 2 |  | 2
| Business Requirements Document (BRD) | Yes | 1 | 1 | 21 |  | 21
| Requirements Traceability Matrix (RTM) |  | 1 | 1 | 2 |  | 2
| Use Case Analysis |  | 1 | 1 | 7 |  | 7
| BRD Review Meeting |  | 1 | 1 | 2 |  | 2
| BRD approval & signoff |  | 1 | 1 | 1 |  | 1
| BRD Baseline |  | 1 | 1 | 0.5 |  | 0.5
| Handover to Design |  | 1 | 1 | 2 |  | 2
| Meeting minutes recorded |  | 1 | 1 | 1 |  | 1
2.2 | Design | [5 empty] | 0
| System and Technical Design Requirements |  | 0 | 1 | 21 |  | 0
| Design review |  | 0 | 1 | 3 |  | 0
| SDD Signoff |  | 1 | 1 | 1 |  | 1
| SDD Baseline |  | 1 | 1 | 0.5 |  | 0.5
| Design to Development Handover |  | 1 | 1 | 2 |  | 2
| Project Kickoff Meeting |  | 1 | 1 | 2 |  | 2
| Assign Roles |  | 1 | 1 | 0.5 |  | 0.5
| Set Work and time schedules |  | 0 | 1 | 1 |  | 0
2.3 | Development | [5 empty] | 0
| Develop Code |  | 0 | 1 | 200 |  | 0
| Code Review |  | 0 | 1 | 2 |  | 0
| Gate Review |  | 0 | 1 | 1 |  | 0
| Unit testing |  | 0 | 1 | 50 |  | 0
| Milestone Build |  | 0 | 1 | 21 |  | 0
| Milestone Review |  | 1 | 1 | 2 |  | 2
| Handover to QA/QC |  | 1 | 1 | 2 |  | 2
| Create final release or product (After QA is complete) |  | 0 | 1 | 14 |  | 0
| Meeting minutes recorded |  | 1 | 1 | 1 |  | 1
| Knowledge Transfer |  | 1 | 1 | 2 |  | 2
2.4 | QA/QC | [5 empty] | 0
| Create Test Plan | Yes | 1 | 1 | 14 |  | 14
| Create Test Cases | Yes | 0 | 1 | 14 |  | 0
| Test Scenarios |  | 1 | 1 | 14 |  | 14
| Run Automated Tests |  | 0 | 1 | 35 |  | 0
| Run Manual Tests |  | 0 | 1 | 35 |  | 0
| Verification and Validation of Tests |  | 1 | 1 | 14 |  | 14
| Sign off |  | 1 | 1 | 2 |  | 2
| Handover to Delivery |  | 1 | 1 | 2 |  | 2
2.5 | Delivery | [5 empty] | 0
| Make product available to customers |  | 0 | 1 | 200 |  | 0
| Provide support for Operations and Maintenance |  | 0 | 1 | 30 |  | 0
3 | Operations Period | [5 empty] | 0
3.1 | Operations and Maintenance | [5 empty] | 0
| System maintenance and Enhancements |  | 0 | 1 | 100 |  | 0
| Obtain feedback from clients |  | 0 |  | 14 |  | 0
3.2 | Deactivate | [5 empty] | 0
| Retire Version Number |  | 0 | 1 | 21 |  | 0
| Implement new Version Number |  | 0 |  | 21 |  | 0
| Replace product (Upgade or new product) |  | 0 | 1 | 500 |  | 0
| Other | [5 empty] | 0
| Templates |  | 1 | 1 | 21 |  | 21
| Checklists |  | 1 | 1 | 7 |  | 7
| Documents |  | 1 | 1 | 14 |  | 14
| Meetings |  | 1 | 1 | 14 |  | 14
| Status |  | 1 | 1 | 5 |  | 5
| Communications |  | 1 | 1 | 21 |  | 21
|  | Items Created | Total BA Hours |  | Max Hours (all items)
|  | 51 | 396.5 |  | 1732 | Hours | 396.5
[8 empty] | Total hours per day |  | 7.5 hour
[8 empty] | Actual work per day |  | 6.5 | 1 hour deducted for email, WOT meetings, breaks, etc.
[8 empty] | Project time: |  | 60 days | 390 hour (Working hours)
Based on 390 Hours I should remove 7 hours worth of items, request another day, or try and fit everything into the 390 days
Note: if you fall behind a little you have the extra hour per day to make up some time.

## Status
Combine items to create a status report
| Item | Deliverable | Create/Use | % Complete | Value | Total Weight | Total | Notes | Level/Weight | Time (H) | Totals
1 | Study Phase
1.1 | Strategic Planning |  |  | 0 | 100 | 0 | 0 | Adjust Total Weight
| Strategic Plan |  | 0 | 100 | 75 | 0 | 0 |  | 1 | 35 | 0
| Strategic Goals |  | 0 | 100 | 25 | 0 | 0 |  | 1 | 7 | 0
1.2 | Enterprise Analysis |  |  | 0 | 100 | 0 | 0 | Adjust Total Weight
| Business Case | Yes | 0 | 100 | 25 | 0 | 0 |  | 0.5 | 10 | 0
| High-Level Description |  | 0 | 100 | 5 | 0 | 0 |  | 1 | 1 | 0
| Project Charter | Yes | 0 | 100 | 45 | 0 | 0 |  | 0.5 | 21 | 0
| Statement of Work | Yes | 0 | 100 | 15 | 0 | 0 |  | 1 | 7 | 0
| Request for Proposal | Yes | 0 | 100 | 10 | 0 | 0 |  | 1 | 1 | 0
| Outsource Development Decision |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 2 | 0
1.3 | Project Management |  |  | 75.95 | 100 | 100 | 75.95 | 100
| Project Checklist |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 2 | 2
| Status meetings |  | 1 | 100 | 20 | 20 | 20 |  | 1 | 10 | 10
| Status reports |  | 1 | 100 | 20 | 20 | 20 |  | 1 | 10 | 10
| Project Plan | Yes | 1 | 100 | 15 | 15 | 15 |  | 1 | 7 | 7
| Project Budgets |  | 1 | 100 | 10 | 10 | 10 |  | 1 | 3.5 | 3.5
| Project timelines |  | 1 | 39 | 5 | 5 | 1.95 |  | 1 | 3.5 | 3.5
| Manage Resources |  | 1 | 25 | 10 | 10 | 2.5 |  | 1 | 7 | 7
| Change Management Plan | Yes | 1 | 20 | 5 | 5 | 1 |  | 1 | 7 | 7
| Risk Management Plan | Yes | 1 | 10 | 5 | 5 | 0.5 |  | 1 | 7 | 7
| Work Breakdown structure | Yes | 1 | 0 | 5 | 5 | 0 |  | 1 | 7 | 7
2 | Implementation Period |  |  | % Complete | Value | Total Weight | Total | Notes
2.1 | Requirements |  |  | 47.75 | 100 | 100 | 23.7 | 100
| Approval to start Reqquirements Gathering |  | 1 | 25 | 1 | 1 | 0.25 |  | 1 | 0.5 | 0.5
| Project Sponsor Meeting |  | 1 | 25 | 5 | 5 | 1.25 |  | 1 | 2 | 2
| Requirements Brainstormign session |  | 1 | 0 | 5 | 5 | 0 |  | 1 | 3 | 3
| Requirements Elicitation |  | 1 | 50 | 10 | 10 | 5 |  | 1 | 21 | 21
| Research |  | 1 | 50 | 5 | 5 | 2.5 |  | 1 | 7 | 7
| Requirements Activities |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 35 | 35
| Requirements Management Plan | Yes | 1 | 80 | 5 | 5 | 4 |  | 1 | 7 | 7
| Requirements Analysis |  | 1 | 30 | 15 | 15 | 4.5 |  | 1 | 14 | 14
| Contect Diagram (Scope) |  | 1 | 5 | 4 | 4 | 0.2 |  | 1 | 2 | 2
| Business Requirements Document | Yes | 1 | 5 | 20 | 20 | 1 |  | 1 | 21 | 21
| Requirements Traceability Matrix | Yes | 1 | 5 | 1 | 1 | 0.05 |  | 1 | 2 | 2
| Use Case Analysis |  | 1 | 100 | 1 | 1 | 1 |  | 1 | 7 | 7
| BRD Review Meeting |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 2 | 2
| BRD approval & signoff |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 1 | 1
| BRD Baseline |  | 1 | 100 | 3 | 3 | 3 |  | 1 | 0.5 | 0.5
| Handover to Design |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 2 | 2
| Meeting minutes recorded |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 1 | 1
|  |  |  | % Complete | Value | Total Weight | Total | Notes
2.2 | Design |  |  | 100 | 100 | 100 |  | 100
| Create system and Technical Design Requirements |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 21 | 21
| Design review |  | 1 | 100 | 35 | 35 | 35 |  | 1 | 3 | 3
| SDD Signoff |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 1 | 1
| SDD Baseline |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 0.5 | 0.5
| Design to Development Handover |  | 1 | 100 | 5 | 5 | 5 |  | 1 | 2 | 2
| Project Kickoff Meeting |  | 1 | 100 | 50 | 50 | 50 |  | 1 | 2 | 2
| Assign Roles |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 0.5 | 0.5
| Set Work and time schedules |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 1 | 1
|  |  |  | % Complete | Value | Total Weight | Total | Notes
2.3 | Development |  |  | 100 | 100 | 100 |  | 100
| Develop Code |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 200 | 200
| Code Review |  | 1 | 100 | 10 | 10 | 10 |  | 1 | 2 | 2
| Gate Review |  | 1 | 100 | 10 | 10 | 10 |  | 1 | 1 | 1
| Unit testing |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 50 | 50
| Milestone Build |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 21 | 21
| Milestone Review |  | 1 | 100 | 15 | 15 | 15 |  | 1 | 2 | 2
| Handover to QA/QC |  | 1 | 100 | 30 | 30 | 30 |  | 1 | 2 | 2
| Create final release or product (After QA is complete) |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 14 | 14
| Meeting minutes recorded |  | 1 | 100 | 20 | 20 | 20 |  | 1 | 1 | 1
| Knowledge Transfer |  | 1 | 100 | 15 | 15 | 15 |  | 1 | 2 | 2
|  |  |  | % Complete | Value | Total Weight | Total | Notes
2.4 | QA/QC |  |  | 100 | 100 | 100 |  | 100
| Create Test Plan | Yes | 1 | 100 | 50 | 50 | 50 |  | 1 | 14 | 14
| Create Test Cases | Yes | 1 | 100 | 0 | 0 | 0 |  | 1 | 14 | 14
| Test Scenarios |  | 1 | 100 | 20 | 20 | 20 |  | 1 | 14 | 14
| Run Automated Tests |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 35 | 35
| Run Manual Tests |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 35 | 35
| Verification and Validation of Tests |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 14 | 14
| Sign off |  | 1 | 100 | 0 | 0 | 0 |  | 1 | 2 | 2
| Handover to Delivery |  | 1 | 100 | 30 | 30 | 30 |  | 1 | 2 | 2
|  |  |  | % Complete | Value | Total Weight | Total | Notes
2.5 | Delivery |  |  | 100 | 100 | 100 |  | 100
| Make product available to customers |  | 1 | 100 | 70 | 70 | 70 |  | 1 | 200 | 200
| Provide support for Operations and Maintenance |  | 1 | 100 | 30 | 30 | 30 |  | 1 | 30 | 30
3 | Operations Period |  |  | % Complete | Value | Total Weight | Total | Notes
3.1 | Operations and Maintenance |  |  | 100 | 100 | 100 |  | 100
| System maintenance and Enhancements |  | 1 | 100 | 50 | 50 | 50 |  | 1 | 100 | 100
| Obtain feedback from clients |  | 1 | 100 | 50 | 50 | 50 |  | 1 | 14 | 14
|  |  |  | % Complete | Value | Total Weight | Total | Notes
3.2 | Deactivate |  |  | 100 | 100 | 100 |  | 100
| Retire Version Number |  | 1 | 100 | 50 | 50 | 50 |  | 1 | 21 | 21
| Implement new Version Number |  | 1 | 100 | 25 | 25 | 25 |  | 1 | 21 | 21
| Replace product (Upgade or new product) |  | 1 | 100 | 25 | 25 | 25 |  | 1 | 500 | 500
|  |  |  | % Complete | Value | Total Weight | Total | Notes
| Other |  |  | 0 | 100 | 0 |  | Adjust Total Weight
| Templates |  | 0 | 50 | 20 | 0 | 0 |  | 1 | 21 | 0
| Checklists |  | 0 | 30 | 12 | 0 | 0 |  | 1 | 7 | 0
| Documents |  | 0 | 1 | 23 | 0 | 0 |  | 1 | 14 | 0
| Meetings |  | 0 | 1 | 15 | 0 | 0 |  | 1 | 14 | 0
| Status |  | 0 | 1 | 10 | 0 | 0 |  | 1 | 5 | 0
| Communications |  | 0 | 1 | 20 | 0 | 0 |  | 1 | 21 | 0
|  |  |  | Total | [5 empty] | Total | Project
|  |  |  | Complete | [5 empty] | Hours | Estimate
|  |  |  | 65.79% | [5 empty] | 1700 | 1534
[5 empty] | Value adds up to 100 |  |  |  |  | Unadjusted | Adjusted

## Historical
Record historical information here:
| Months | Small | Medium | Large |  |  |  |  | # of
Project | 0 to 3 | 3 to 6 | 6 to 12 | 12 to 24 | Phases | Hours | Methodology | Prototypes | Requirements | RTM | BRD | SRD | Charter | WBS | RMP | User Guide | Test Cases | Use Case | Diagrams
Enhancement | [5 empty] | 390 | TBD | No | 1 | No | Yes | Yes | No | No | No | No | Yes
Small | [5 empty] | 650 | TBD | No | 5 | Yes | Yes | Yes | No | No | No | No | Yes
Medium | [5 empty] | 1300 | TBD | Yes | 25 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Large | [5 empty] | 2600 | TBD | Yes | 50 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Project 1 |  |  |  |  | 1 |  | Spiral | No | 2 | No | No | No | No | No | No | Yes | No | No | No
Project 2 |  |  |  |  | 3 |  | Waterfall | No | 17 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes
Project 3 |  |  |  |  | 5 |  | Agile | Yes | 19 | Yes | Yes | No | No | Yes | No | Yes | No | Yes | Yes

## Templates
Name | Item | Size | Format | Project | locations | [6 empty] | References
Examples: |  |  |  |  | USB | Blog | SkyDrive | Google Docs | Backup | Binder | Other
| Business Case |  |  |  | x
BRD Template 1 | Business Requirements Document | Extra | Word | Project 1 | x |  | x | x | x |  | Share
BRD_Simple_Template | Business Requirements Document | lite | Excel | Project 2 | x |  | x | x | x
BRD_Small_Template | Business Requirements Document | Small | Word | Project 3 | x | x | x | x | x
BRD_Template | Business Requirements Document | Regular | Word | Project 1, Project 2 | x |  | x | x | x
Business Requirements Document Template | Business Requirements Document | Regular | Word | Project 1, Project 2 | x |  |  |  | x |  | Share
Requirements Tracebility Matrix Template | Requirements Traceability Matrix | RTM | Excel | Project 1, Project 2 | x | x | x | x | x | x
RMP Template | Requirements Management Plan | RMP | Word | Project 1, Project 2 | x |  | x | x | x
| Mindmap |  | Paper | [5 empty] | x
| Project Charter | Regular | Word |  | x |  |  |  | x
SWOT Template | SWOT analysis | Regular | Word |  | x | x |  |  | x | x
WBS_Template | Work Breakdown structure | WBS | WBSCharpro |  | x |  |  |  | x | x
WBS_Visio_Template | Work Breakdown structure | WBS | Visio | N/A | x |  |  |  | x | x
Communication Plan Template 1 | Communication plan | Small | Word |  | x | x | x | x | x | x
Communication Plan Template 2 | Communication plan | Regular | Word |  | x |  | x | x | x
Test Case Template | Test Case Template |  | Word | [5 empty] | x | x
Status | Status spreadsheet | Custom | Excel |  | x |  |  |  | x |  | HDD
Statement of Work Template | Statement of work | Regular | Excel |  | x |  |  |  | x |  | Share
Task List | Project Task list | Custom | Excel |  | x |  |  |  | x |  | Share
Project Deliverables | Project Deliveriables document | Custom | Word | [6 empty] | x
Project use case specification | Project use case specification document | Regular | Word | [6 empty] | x
Development Plan Template | Development Plan | Regular | Word | [6 empty] | x |  | External Vendor
Business Case Template | Business Case | Regular | Word | [6 empty] | x
QP 111 - Design & Development | ISO Design & Development Document | Regular | Word | [6 empty] | x | Share
OPM Checklist | Operational Procedure Manual | Regular | Word |  | x |  |  |  | x | x | Share
BA Project Checklist template | Camouflage Software Project Checklist | Regular | Word |  | x |  |  |  | x | x | Share
Go-No Go Decision DB Patch Management | Decision Document | Regular | Word | [5 empty] | x | x | Share
Risk Assessment Template | Risk Assessment Document | Regular | Word | [5 empty] | x |  | Share
Change Management Template | Change Management Document | Regular | Word | [5 empty] | x |  | Share
Guidelines Document Template | Guidelines document | Regular | Word | [5 empty] | x |  | Local

## Activity List
Sample activity list with project codes.
Code | Item | Description
1 | Meetings
1.1 | Project Sponsor Meetings | Initial project meeting or combined with another meeting
1.2 | Requirements Brainstorming Session | Group Meeting
1.3 | Requirements Elicitation | Solo or group meetings
1.4 | Requirements Analysis | Analysis and Review
1.5 | Use Case Analysis | Analysis and Review
1.6 | BRD Review Meeting | Review, Update, Approve, and signoff
1.7 | Handover meeting | Review documentation and handver to phase or group
2 | Documentation
2.1 | BRD | Business Requirements Document
2.2 | RPM | Requirements Management Plan
2.3 | RTM | Requirements Traceability Matrix
2.4 | Meeting Minutes | Record and add to repositiry
3 | Approvals
3.1 | Approval to start requirements gathering | Should be first activity
3.2 | BRD approval and signoff | with review meeting
3.3 | BRD Baseline Document | After apporval and signoff
3.4 | Requirements Handover | i.e: Handver with review meeting
4 | Other
4.1 | Diagrams | Other diagrams
4.2 | Templates | Other templates
4.3 | lists | Other lists
4.4 | Checklists | Other checklists
4.5 | Tasks | Other tasks
4.6 | Meetings | Other meetings
4.7 | Communication | Additional communication

## Stakeholders
Role
Projects |  | Client | Sponsor | Team Lead | PM | BA | QA Lead | QA Tester | End User | Other | Developer 1 | Developer 2
Project 1 |  | ABC Corp. | <<Sponsor>> | <<Team Lead>> | <<PM>> | <<BA>> | <<QA Lead>> | <<Tester>> | <<User>> | <<Other>> | <<Developer>> | <<Developer>>
Project 2 |  | ACME Inc. | <<Sponsor>> | <<Team Lead>> | <<PM>> | <<BA>> | <<QA Lead>> | <<Tester>> | <<User>> | <<Other>> | <<Developer>> | <<Developer>>
Project 3 |  | 123 ltd. | <<Sponsor>> | <<Team Lead>> | <<PM>> | <<BA>> | <<QA Lead>> | <<Tester>> | <<User>> | <<Other>> | <<Developer>> | <<Developer>>
Project 4 |  | Generic Co. | <<Sponsor>> | <<Team Lead>> | <<PM>> | <<BA>> | <<QA Lead>> | <<Tester>> | <<User>> | <<Other>> | <<Developer>> | <<Developer>>

## Calculations
Enter your project calculations here.
|  | EV | - | PV
0 | SV | 1 |  | 1
|  | EV | /
1 | SPI | 1 |  | 1
|  | EV | - | AC
0 | CV | 1 |  | 1
|  | EV | / | AC
0 | CPI | 1 |  | 1
Pert weighted average
Best time + (4 x average time) + worst time / 6